## Functions
Function Name | Classification | Status | Assignee | Required Effort/ Priority Level | Priority for Qual | Specs Target Date | Testing Target Date
AE_Assess | Assess | Ready to submit PR once access to clindata confirmed | Chelsea Dickens | High - by 3/1 | Normal approx | 2022-12-09 | 2022-12-12
AE_Map_Adam | Map | Not to be qualified
AE_Map_Raw | Map | Working on specs | Colleen McLaughlin | High - by 3/1 | Normal approx | 2022-12-14
Analyze_Fisher | Analyze | To be qualified after 3/1
Analyze_Identity | Analyze | To be qualified after 3/1
Analyze_NormalApprox | Analyze | To be qualified (not started) | Chelsea Dickens | High - by 3/1 | Normal approx
Analyze_NormalApprox_PredictBounds | Analyze | To be qualified (not started) |  | Medium
Analyze_Poisson | Analyze | To be qualified after 3/1
Analyze_Poisson_PredictBounds | Analyze | To be qualified after 3/1
Analyze_QTL | Analyze | To be qualified (not started) | Chelsea Dickens | High - by 3/1 | QTL
CheckInputs | Utility - QC | To be qualified after 3/1 |  | Low
Consent_Assess | Assess | Qualified
Consent_Map_Raw | Map | Not to be qualified
ConsolidateStrata | Utility - Workflow | Not to be qualified
DataChg_Assess | Assess | To be qualified (not started) | Chelsea Dickens | High - by 3/1 | Normal approx | 2022-12-09
DataChg_Map_Raw | Map | Working on specs | Colleen McLaughlin | High - by 3/1 | Normal approx | 2022-12-14
DataEntry_Assess | Assess | To be qualified (not started) | Chelsea Dickens | High - by 3/1 | Normal approx | 2022-12-09
DataEntry_Map_Raw | Map | Working on specs | Colleen McLaughlin | High - by 3/1 | Normal approx | 2022-12-14
Disp_Assess | Assess | In progress | Chelsea Dickens | High - by 3/1 | Normal approx and QTL | 2022-12-09 | 2022-12-12
Disp_Map_Raw | Map | Working on specs | Colleen McLaughlin | High - by 3/1 | Normal approx and QTL | 2022-12-14
FilterData | Utility - Data Transformation | To be qualified after 3/1 |  | Low
FilterDomain | Utility - Data Transformation | To be qualified (not started) | Chelsea Dickens | High - by 3/1
Flag | Flag | Not to be qualified
Flag_Fisher | Flag | To be qualified after 3/1
Flag_NormalApprox | Flag | To be qualified (not started) | Chelsea Dickens | High - by 3/1 | Normal approx
Flag_Poisson | Flag | To be qualified after 3/1
Flag_QTL | Flag | To be qualified (not started) | Chelsea Dickens | High - by 3/1 | QTL
generate_md_table | Utility - Documentation | Not to be qualified
Get_Enrolled | Utility - Data Transformation | To be qualified (not started) | Colleen McLaughlin | High - by 3/1
IE_Assess | Assess | Qualified
IE_Map_Raw | Map | Not to be qualified
is_mapping_valid | Metadata | To be qualified after 3/1 |  | Low
LB_Assess | Assess | In progress | Chelsea Dickens | High - by 3/1 | Normal approx | 2022-12-09 | 2022-12-12
LB_Map_Raw | Map | Working on specs | Colleen McLaughlin | High - by 3/1 | Normal approx | 2022-12-14
Make_Snapshot | Data Model | To be qualified - likely last once all other components are qualified |  | Low
MakeStratifiedAssessment | Utility - Workflow | Not to be qualified
MakeWorkflowList | Utility - Workflow | To be qualified after 3/1 |  | Low
MergeSubjects | Utility - Data Transformation | To be qualified (not started) | Chelsea Dickens | High - by 3/1
parse_data_mapping | Utility - Documentation | Not to be qualified
parse_data_spec | Utility - Documentation | Not to be qualified
ParseWarnings | Utility - Workflow | Not to be qualified
PD_Assess | Assess | In progress | Chelsea Dickens | High - by 3/1 | Normal approx and QTL | 2022-12-09 | 2022-12-12
PD_Map_Raw | Map | Working on specs | Colleen McLaughlin | High - by 3/1 | Normal approx and QTL | 2022-12-14
QueryAge_Assess | Assess | To be qualified (not started) | Chelsea Dickens | High - by 3/1 | Normal approx | 2022-12-09
QueryAge_Map_Raw | Map | Working on specs | Colleen McLaughlin | High - by 3/1 | Normal approx | 2022-12-14
QueryRate_Assess | Assess | To be qualified (not started) | Chelsea Dickens | High - by 3/1 | Normal approx | 2022-12-09
QueryRate_Map_Raw | Map | Working on specs | Colleen McLaughlin | High - by 3/1 | Normal approx | 2022-12-14
RemoveInvalidSubjectIDs | Utility - Data Transformation | Not to be qualified
ReportHelpers | Utility - Reporting | Not to be qualified
RunQTL | Utility | Not to be qualified
RunStep | Utility - Workflow | To be qualified after 3/1 |  | Low
RunStratifiedWorkflow | Utility - Workflow | Not to be qualified
RunWorkflow | Utility - Workflow | To be qualified after 3/1 |  | Low
SaveQTL | Utility | Not to be qualified
Study_Assess | Data Model | To be qualified - likely last once all other components are qualified |  | Low
Study_AssessmentReport | Reporting | Not to be qualified
Study_Report | Reporting | Not to be qualified
Study_Table | Reporting | Not to be qualified
Summarize | Summarize | To be qualified (not started) | Colleen McLaughlin | High - by 3/1
tests-assess_helpers | Utility | Not to be qualified
tests-map_raw_helpers | Utility | Not to be qualified
Transform_Count | Transform | To be qualified (not started) | Colleen McLaughlin | High - by 3/1
Transform_Rate | Transform | To be qualified (not started) | Colleen McLaughlin | High - by 3/1
Visualize_Scatter | Visualize | Not to be qualified
Visualize_Score | Visualize | Not to be qualified
Visualize_Workflow | Visualize | Not to be qualified
Note on B54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Colleen McLaughlin (Contractor) made some updates here - mostly to add another level to the Utility classification. Also removed some rows for functions that we don't need to track (pipe, gsm-package, etc).

## Specs - Batch 1
Spec # | Test # | Test_Subtest # | Function Name | Description | Risk | Impact | Spec Status | Test Status | Comments
1 | 1 | T1_1, T1_2, T1_3 | AE_Assess | Given correct input data an Adverse Event assessment can be done using the poisson method | High | High | Approved | Approved
1 | 2 | T1_4, T1_5, T1_6 | AE_Assess | Given correct input data an Adverse Event assessment can be done using the identity method | High | High | Approved | Approved
1 | 3 | T1_1, T1_2, T1_3, T1_4, T1_5, T1_6 | AE_Assess | Assessments are correctly grouped by a grouping variable such as site or country for KRIs and study for QTLs when applicable | Low | High | Approved | Approved
1 | 4 | T1_1, T1_2, T1_3, T1_4, T1_5, T1_6 | AE_Assess | Given correct input data flags will correctly be applied to records that meet flagging criteria, including custom thresholding | Medium | High | Approved | Approved
1 | 5 | T1_3, T1_6 | AE_Assess | Given subset input data an Adverse Event assessment can be done | Medium | Medium | Approved | Approved
1 | 6 |  | AE_Assess | Given correct input data an Adverse Event assessment can be done using the normal approximation method | High | High | Ready for Review | In Revision
11 |  |  | AE_Map_Raw | Given correct metadata, the raw data for an AE assessment can be correctly mapped to an analysis-ready input dataset. | Medium | High | Ready for Review |  | Good. We probably need more qualification for the mapping functions. I'll draft them here. Thanks. - Kai
19 |  |  | Analyze_NormalApprox
20 |  |  | Analyze_QTL
4 | 1 |  | Consent_Assess | Given correct input data a Consent assessment can be done | High | High | Approved | Complete
4 | 2 |  | Consent_Assess | Assessments are correctly grouped by a grouping variable such as site or country for KRIs and study for QTLs when applicable | Low | High | Approved | Complete
4 | 3 |  | Consent_Assess | Given correct input data flags will correctly be applied to records that meet flagging criteria, including custom thresholding | Medium | High | Approved | Complete
4 | 4 |  | Consent_Assess | Given subset input data a Consent assessment can be done | Medium | Medium | Approved | Complete
7 |  |  | DataChg_Assess | Given correct input data a data change rate assessment can be done using the fisher method | High | High | Ready for Review
7 |  |  | DataChg_Assess | Given correct input data a data change rate assessment can be done using the identity method | High | High | Ready for Review
7 |  |  | DataChg_Assess | Given correct input data a data change rate assessment can be done using the normal approximation method | High | High | Ready for Review
7 |  |  | DataChg_Assess | Assessments are correctly grouped by a grouping variable such as site or country for KRIs and study for QTLs when applicable | Low | High | Ready for Review
7 |  |  | DataChg_Assess | Given correct input data flags will correctly be applied to records that meet flagging criteria, including custom thresholding | Medium | High | Ready for Review
7 |  |  | DataChg_Assess | Given subset input data a Data Change assessment can be done | Medium | Medium | Ready for Review
12 |  |  | DataChg_Map_Raw | Given correct metadata, the raw data for a Data Change Rate assessment can be correctly mapped to an analysis-ready input dataset. | Medium | High | Ready for Review |  | Good
8 |  |  | DataEntry_Assess | Given correct input data a Data Entry Lag assessment can be done using the fisher method | High | High | Ready for Review
8 |  |  | DataEntry_Assess | Given correct input data a Data Entry Lag assessment can be done using the identity method | High | High | Ready for Review
8 |  |  | DataEntry_Assess | Given correct input data a Data Entry Lag assessment can be done using the normal approximation method | High | High | Ready for Review
8 |  |  | DataEntry_Assess | Assessments are correctly grouped by a grouping variable such as site or country for KRIs and study for QTLs when applicable | Low | High | Ready for Review
8 |  |  | DataEntry_Assess | Given correct input data flags will correctly be applied to records that meet flagging criteria, including custom thresholding | Medium | High | Ready for Review
8 |  |  | DataEntry_Assess | Given subset input data a Data Entry Lag assessment can be done | Medium | Medium | Ready for Review
13 |  |  | DataEntry_Map_Raw | Given correct metadata, the raw data for a Data Entry Lag assessment can be correctly mapped to an analysis-ready input dataset. | Medium | High | Ready for Review |  | Good
5 |  |  | Disp_Assess | Given correct input data a Disposition assessment can be done using the fisher method | High | High | Approved | Approved
5 |  |  | Disp_Assess | Given correct input data a Disposition assessment can be done using the identity method | High | High | Approved | Approved
5 |  |  | Disp_Assess | Assessments are correctly grouped by a grouping variable such as site or country for KRIs and study for QTLs when applicable | Low | High | Approved | Approved
5 |  |  | Disp_Assess | Given correct input data flags will correctly be applied to records that meet flagging criteria, including custom thresholding | Medium | High | Approved | Approved
5 |  |  | Disp_Assess | Given subset input data a Disposition assessment can be done | Medium | Medium | Approved | Approved
5 |  |  | Disp_Assess | Given correct input data a Disposition assessment can be done using the normal approximation method | High | High | Ready for Review | In Revision
14 |  |  | Disp_Map_Raw | Given correct metadata, the raw data for a Disposition assessment can be correctly mapped to an analysis-ready input dataset. | Medium | High | Ready for Review |  | Good
21 |  |  | FilterDomain
22 |  |  | Flag_NormalApprox
23 |  |  | Flag_QTL
24 |  |  | Get_Enrolled | Given correct input data and metadata, the correct number of enrolled participants per study can be derived. | Low | High | Ready for Review
24 |  |  | Get_Enrolled | Given correct input data and metadata, the correct number of sites per study can be derived. | Low | High | Ready for Review
24 |  |  | Get_Enrolled | Given correct input data and metadata, the correct number of enrolled participants per site can be derived. | Low | High | Ready for Review
3 |  |  | IE_Assess | Given correct input data an Inclusion/Exclusion assessment can be done | High | High | Approved | Complete
3 |  |  | IE_Assess | Assessments are correctly grouped by a grouping variable such as site or country for KRIs and study for QTLs when applicable | Low | High | Approved | Complete
3 |  |  | IE_Assess | Given correct input data flags will correctly be applied to records that meet flagging criteria, including custom thresholding | Medium | High | Approved | Complete
3 |  |  | IE_Assess | Given subset input data an Inclusion/Exclusion assessment can be done | Medium | Medium | Approved | Complete
6 |  |  | LB_Assess | Given correct input data a Labs assessment can be done using the fisher method | High | High | Approved | Approved
6 |  |  | LB_Assess | Given correct input data a Labs assessment can be done using the identity method | High | High | Approved | Approved
6 |  |  | LB_Assess | Assessments are correctly grouped by a grouping variable such as site or country for KRIs and study for QTLs when applicable | Low | High | Approved | Approved
6 |  |  | LB_Assess | Given correct input data flags will correctly be applied to records that meet flagging criteria, including custom thresholding | Medium | High | Approved | Approved
6 |  |  | LB_Assess | Given subset input data a Labs assessment can be done | Medium | Medium | Approved | Approved
6 |  |  | LB_Assess | Given correct input data a Labs assessment can be done using the normal approximation method | High | High | Ready for Review | In Revision
15 |  |  | LB_Map_Raw | Given correct metadata, the raw data for a Labs assessment can be correctly mapped to an analysis-ready input dataset. | Medium | High | Ready for Review |  | Good
25 |  |  | MergeSubjects
2 |  |  | PD_Assess | Given correct input data a Protocol Deviation assessment can be done using the poisson method | High | High | Approved | Approved
2 |  |  | PD_Assess | Given correct input data a Protocol Deviation assessment can be done using the identity method | High | High | Approved | Approved
2 |  |  | PD_Assess | Assessments are correctly grouped by a grouping variable such as site or country for KRIs and study for QTLs when applicable | Low | High | Approved | Approved
2 |  |  | PD_Assess | Given correct input data flags will correctly be applied to records that meet flagging criteria, including custom thresholding | Medium | High | Approved | Approved
2 |  |  | PD_Assess | Given subset input data a Protocol Deviation assessment can be done | Medium | Medium | Approved | Approved
2 |  |  | PD_Assess | Given correct input data a Protocol Deviation assessment can be done using the normal approximation method | High | High | Ready for Review | In Revision
16 |  |  | PD_Map_Raw | Given correct metadata, the raw data for a Protocol Deviation assessment can be correctly mapped to an analysis-ready input dataset. | Medium | High | Ready for Review |  | Good
9 |  |  | QueryAge_Assess | Given correct input data a Query Age assessment can be done using the fisher method | High | High | Ready for Review
9 |  |  | QueryAge_Assess | Given correct input data a Query Age assessment can be done using the identity method | High | High | Ready for Review
9 |  |  | QueryAge_Assess | Given correct input data a Query Age assessment can be done using the normal approximation method | High | High | Ready for Review
9 |  |  | QueryAge_Assess | Assessments are correctly grouped by a grouping variable such as site or country for KRIs and study for QTLs when applicable | Low | High | Ready for Review
9 |  |  | QueryAge_Assess | Given correct input data flags will correctly be applied to records that meet flagging criteria, including custom thresholding | Medium | High | Ready for Review
9 |  |  | QueryAge_Assess | Given subset input data a Query Age assessment can be done | Medium | Medium | Ready for Review
17 |  |  | QueryAge_Map_Raw | Given correct metadata, the raw data for a Query Age assessment can be correctly mapped to an analysis-ready input dataset. | Medium | High | Ready for Review |  | Good
10 |  |  | QueryRate_Assess | Given correct input data a Query Rate assessment can be done using the fisher method | High | High | Ready for Review
10 |  |  | QueryRate_Assess | Given correct input data a Query Rate assessment can be done using the identity method | High | High | Ready for Review
10 |  |  | QueryRate_Assess | Given correct input data a Query Rate assessment can be done using the normal approximation method | High | High | Ready for Review
10 |  |  | QueryRate_Assess | Assessments are correctly grouped by a grouping variable such as site or country for KRIs and study for QTLs when applicable | Low | High | Ready for Review
10 |  |  | QueryRate_Assess | Given correct input data flags will correctly be applied to records that meet flagging criteria, including custom thresholding | Medium | High | Ready for Review
10 |  |  | QueryRate_Assess | Given subset input data a Query Rate assessment can be done | Medium | Medium | Ready for Review
18 |  |  | QueryRate_Map_Raw | Given correct metadata, the raw data for a Query Rate assessment can be correctly mapped to an analysis-ready input dataset. | Medium | High | Ready for Review |  | Good
26 |  |  | Summarize | Given correct input data, a summary data frame can be generated that selects the correct columns. | Low | Medium | Ready for Review
26 |  |  | Summarize | Given correct input data, a summary data frame can be generated and sorted appropriately. | Low | Medium | Ready for Review
27 |  |  | Transform_Count
28 |  |  | Transform_Rate

## High-Level Schedule
Function Class | Target Qual Completion Date
Analyze
Assess
Data Model
Flag
Map
Metadata
Reporting
Summarize
Transform
Utility
Utility - Data Transformation
Utility - Documentation
Utility - QC
Utility - Reporting
Utility - Workflow
Visualize
Note on D58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Colleen McLaughlin (Contractor) made some updates here - mostly to add another level to the Utility classification. Also removed some rows for functions that we don't need to track (pipe, gsm-package, etc).